## Sheet1
Phase | Task | Owner | Tools | Output
1. Infra Setup | Define and provision infrastructure with Terraform | DevOps | Terraform, Azure CLI | AKS, ACR, Key Vault, PostgreSQL, VNet deployed
1. Infra Setup | Configure resource group, networking (VNet/Subnets) | DevOps | Terraform | Secured private network setup
1. Infra Setup | Enable monitoring, RBAC, diagnostics | DevOps | Azure Monitor, Log Analytics | Infra observability enabled
2. Containerization | Dockerize Spring Boot backend and Angular frontend | Developers | Docker, Maven, npm | Docker images for services created
2. Containerization | Push container images to Azure Container Registry (ACR) | DevOps | ACR | ACR hosts app images
3. Helm Integration | Create Helm charts for backend and frontend | DevOps | Helm | Versioned, environment-ready Helm charts
3. Helm Integration | Parameterize values for dev/stage/prod | DevOps | Helm | Reusable Helm templates
4. Argo CD Setup | Install Argo CD in AKS cluster | DevOps | Helm, kubectl | GitOps controller running
4. Argo CD Setup | Link Argo CD with Git repository | DevOps | Argo CD UI/CLI | Auto-deploy enabled from Git
4. Argo CD Setup | Create App-of-Apps or per-service Argo apps | DevOps | Argo CD, Helm | Declarative deployment manifests
5. CI/CD Pipeline | Configure GitHub Actions for build, test, Docker build | DevOps | GitHub Actions | CI pipelines in place
5. CI/CD Pipeline | Add deployment stage to push Helm changes to Git | DevOps | GitHub Actions | GitOps trigger for Argo CD
6. Data Migration | Export on-prem PostgreSQL data using pg_dump | DBA | pg_dump, pg_restore | Dump files generated
6. Data Migration | Import data into Azure PostgreSQL Flexible Server | DBA | Azure CLI, pg_restore | Production data available in cloud
6. Data Migration | Re-index documents in Azure (OpenSearch or Cognitive Search) | DevOps/Data Eng. | Logstash/Azure Search SDK | Search infrastructure migrated
7. Cutover & Validate | Switch DNS to point to Azure Ingress | DevOps/NetOps | Azure DNS, App Gateway | Production traffic routed to Azure
7. Cutover & Validate | Validate service health and logs | QA/DevOps | Azure Monitor, Grafana | Success criteria met
7. Cutover & Validate | Decommission on-prem infra after stabilization | Infra/IT Ops | Manual | Cost optimization and resource clean-up